## GanttChart
Automatic Attendance System Project Schedule
| Project Start Date | 2022-10-03 |  |  |  | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
| Project Lead | [5 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05
 | time axis 2022-10-03 to 2022-12-11
WBS | TASK |  | PREDECESSOR | START | END | % DONE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Understanding deliverables and required outcome |  |  | 2022-10-03 | 2022-10-09 | 100%
2 | Gathering information regarding project and technologies |  |  | 2022-10-10 | 2022-10-16 | 100%
3 | Designing and database |  |  | 2022-10-17 | 2022-10-23 | 5%
4 | Analyze and extract data from images using OpenCV |  |  | 2022-10-24 | 2022-10-30 | 0%
5 | Database integration |  |  | 2022-10-31 | 2022-11-06 | 0%
6 | Screen 1 code implementation |  |  | 2022-11-07 | 2022-11-13 | 0%
7 | Screen 2 code implementation |  |  | 2022-11-14 | 2022-11-20 | 0%
8 | Screen 3 code implementation |  |  | 2022-11-21 | 2022-11-27 | 0%
9 | Testing and adjusting |  |  | 2022-11-28 | 2022-12-04 | 0%
10 | Project Presentation |  |  | 2022-12-05 | 2022-12-11 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).